## Summarising All_Activities_15-3
Activity | Description | Predecessor | Time | EST | EFT | LST | LFT | Slack
A | Details of Discussion by BOD |  | 5 | 0 | 5 | 0 | 5 | 0
B | Request Prototypes | A | 10 | 5 | 15 | 5 | 15 | 0
C | Marketing Program | A | 8 | 5 | 13 | 13 | 21 | 8
D | Prepare Instructions | B | 7 | 15 | 22 | 21 | 28 | 6
E | Design Packaging | B | 9 | 15 | 24 | 15 | 24 | 0
F | Approval from President | C | 3 | 13 | 16 | 21 | 24 | 8
G | Saleforce Training | D,E | 2 | 24 | 26 | 34 | 36 | 10
H | Develop Information Guide | D,F | 8 | 22 | 30 | 28 | 36 | 6
I | Hire to Potray Mighty Monkeys | F | 8 | 16 | 24 | 28 | 36 | 12
J | Manufacture POS Racks | E,F | 12 | 24 | 36 | 24 | 36 | 0

## Critical_Path_15-3
|  | Paths | Duration
|  | A-B-D-G | 24
|  | A-B-D-H | 30
|  | A-B-E-G | 26
|  | A-B-E-J | 36
|  | A-C-F-H | 24
|  | A-C-F-J | 28
|  | A-C-F-I | 24
[7 empty] | 24 | 26
[5 empty] | 15 | 22 | G | 2 |  | Legend
[5 empty] | D | 7 | 34 | 36 |  | EST | EFT
[5 empty] | 21 | 28 |  |  |  | Activ. | time
|  |  | 5 | 15 | [5 empty] | LST | LFT
|  |  | B | 10
|  |  | 5 | 15 |  |  | 22 | 30
[7 empty] | H | 8
[5 empty] | 15 | 24 | 28 | 36
0 | 5 |  |  |  | E | 9 |  |  | Finish
A | 5 |  |  |  | 15 | 24
0 | 5
[7 empty] | 24 | 36
|  |  | 5 | 13 |  |  | J | 12
|  |  | C | 8 |  |  | 24 | 36
|  |  | 13 | 21 | 13 | 16
[5 empty] | F | 3
[5 empty] | 21 | 24 | 16 | 24
[7 empty] | I | 8
[7 empty] | 28 | 36

## D & E Questions_15-3
D.) If Amy starts working immediately, it will take 36 days for her to complete this project.
E.) Yes, because the prototyping activity is on the critical path line. So, by creating prototypes in only 8 days instead of 10 days will reduce the total time it takes to complete the project from 36 days to 34 days.
|  |  |  | o | m | c
|  |  |  | 2 | 3 | 5 | =
| 1 | 1000 | 10750 | 3 | 4 | 6
| 3 | 500 | 750
| 5 | 250 | 1
| 4 | 750 | -2979
| 8 | 500